## Execution Tracker
Section | TC ID | Scenario | Preconditions | Test Steps | Expected Result | Priority | Status | Actual Result | Defect ID | Executed On | Notes
6.1 Authentication & authorization | TC-A01 | Garage owner signup & onboarding checklist | None | 1. Sign up with a new email 2. Verify email 3. Complete onboarding: business profile, Twilio number assignment, add first customer 4. Reach dashboard | Account created; checklist ticks off each step; dashboard loads with the assigned Twilio number visible | P0 | Pass | Signup OK (surathpar+revlooptest@gmail.com); no email verification required. Onboarding checklist ticked: address, Google review link, services, first customer. 'Garage approved' and 'Dedicated SMS number assigned' remain UNTICKED — admin number pool is EMPTY ('No free numbers in pool'), so no number can be assigned. | BUG-006 | 2026-10-01
6.1 Authentication & authorization | TC-A02 | Staff invite & role restrictions | Owner account active | 1. Owner invites staff by email 2. Staff accepts & logs in 3. Use CRM, calendar, conversations 4. Try Settings, Billing, SMS Templates | Allowed areas work; Settings/Billing/Templates return 403 (not just hidden links) | P0 | Pass | Retest 2026-10-02: staff direct-URL nav to /settings,/templates,/automations,/billing,/admin,/sales each shows full-page 403 'Access denied' - no redirect to /calendar. BUG-001 FIXED. | BUG-001 | 2026-10-02
6.1 Authentication & authorization | TC-A03 | Staff direct-URL access to billing | Staff logged in | Navigate directly to the billing/settings URL | 403 page; attempt written to audit log | P0 | Pass | Retest 2026-10-02: all six staff 403 attempts logged as access.denied with actor/role/path/garage/time. BUG-001/BUG-002 FIXED. | BUG-001, BUG-002 | 2026-10-02
6.1 Authentication & authorization | TC-A04 | Cross-tenant isolation | Garages A and B exist | As Garage A owner, open a Garage B customer/booking URL by editing the ID | 403; no Garage B data leaked; audit log entry | P0 | Pass | Retest 2026-10-02: cross-tenant customer URL returns 403 'record belongs to another garage' (not 'not found'); access.denied.cross-tenant audit entries written. BUG-002/BUG-003 FIXED. | BUG-002, BUG-003 | 2026-10-02
6.1 Authentication & authorization | TC-A05 | Admin impersonation with audit | Admin account | 1. Admin starts impersonation of a garage owner 2. Perform an action 3. End impersonation | Visible impersonation banner; every action logged under the admin's identity | P1 | Pass | Support login required a reason (>=10 chars); banner 'Support mode: viewing Demo Auto Toronto. All actions are audited.' shown with Exit button; start/stop logged under admin identity. |  | 2026-10-01
6.1 Authentication & authorization | TC-A06 | Session timeout & password reset | Active login | 1. Idle past the timeout 2. Use 'forgot password' and reset via email link | Logged out after timeout; old sessions invalidated after reset | P1 | Pass | Retest 2026-10-02: 'Forgot password?' link on /login; /forgot-password shows 1-hour one-time-link wording; /reset-password form present (no reset submitted). SESSION_IDLE_MINUTES setting exists in Integrations (default shows 'not set'). BUG-004/BUG-005 FIXED (UI layer). ¦ Round-3 retest 2026-10-02: Integrations now shows 'not set - using default 60' for SESSION_IDLE_MINUTES (also 14/7 for trial/grace). BUG-005 fully fixed. | BUG-004, BUG-005 | 2026-10-02
6.2 CRM, vehicles & CSV import | TC-B01 | Add / edit / search customer | Owner logged in | 1. Add customer (name, phone, email) 2. Edit phone 3. Search by name and by phone | Customer saved; edits persist; search finds it both ways | P0 | Pass | Retest 2026-10-02: customer Edit dialog (name/phone/email) works; duplicate phone rejected; customer.updated audit entries written. BUG-007 FIXED. | BUG-007 | 2026-10-02
6.2 CRM, vehicles & CSV import | TC-B02 | Vehicle + service history | Customer exists | 1. Add vehicle (make/model/year/plate/km) 2. Add service record (date, job, cost) 3. Open history timeline | Vehicle linked to customer; service history shows newest-first with totals | P0 | Pass | Added 2019 Honda Civic (QA2019, 45,200 km) + 2 service records via completing appointments (Oil & filter $89.95, Tire change $120.00). SERVICE HISTORY newest-first with per-record costs. Notes: no aggregate Total row; history shows completing user (Dev Patel) not assigned tech; past-dated appointments rejected so records only via completing future appointments. |  | 2026-10-01
6.2 CRM, vehicles & CSV import | TC-B03 | CSV import — happy path | Clean CSV with 10 new customers | Upload via Import; map columns; run | 10 customers created; import summary shows 10 added / 0 skipped / 0 errors | P0 | Pass | All 10 customers imported with correct data (QA Import 01-10, phones +15550103101-110, 2016-2025 Honda Civic, plates IMP001-IMP010). Verified by owner upload + Kavi read-back on 2026-10-01. ¦ Round-3 retest 2026-10-02: Customers page shows total count matching dashboard (19=19). BUG-020 fixed. |  | 2026-10-02
6.2 CRM, vehicles & CSV import | TC-B04 | CSV import — duplicate phones skipped | 2 rows share a phone with existing customers | Upload and run import | Duplicates skipped or merged per spec; report shows exactly which rows and why | P0 | Pass | Re-upload of b04_dupes.csv correctly flagged all 3 rows as "already exist" duplicates (row two, row three, row four). Read-back verified exactly 1 record per phone (+14165551000, +14165551001, +15550103121) and customer total steady at 17 — no duplicate records created. Manual Quick-add also blocks duplicates ("This phone number already belongs to a customer."). |  | 2026-10-01
6.2 CRM, vehicles & CSV import | TC-B05 | CSV import — malformed rows | CSV with 2 bad rows (missing phone, bad date) | Upload and run import | Bad rows listed with row numbers and reasons; valid rows still import | P1 | Pass | Retest 2026-10-02: import now rejects invalid year - 'Row 3: Vehicle needs make, plate and a valid year (1900-2100); got year notayear. Row not imported.' 2 valid rows imported, no customer created for bad row. BUG-019 FIXED. | BUG-019 | 2026-10-02
6.2 CRM, vehicles & CSV import | TC-B06 | CASL consent captured at customer creation | Owner logged in | Add a customer and tick the consent checkbox | Consent ledger shows entry: customer, source 'manual', timestamp, opt-in=true | P0 | Pass | Created 'QA B06 Test' (+15550106666) via Quick add with SMS consent ticked. Profile Consent log tab shows EXPRESS entry ('staff attestation'), timestamp Oct 1 7:45 PM, accepted=true, full consent text. (Source labeled 'staff attestation' rather than 'manual'.) |  | 2026-10-01
6.3 Appointments, booking link & SMS reminders | TC-C01 | Create appointment in calendar | Owner logged in | Create appointment for tomorrow 10:00 AM with customer + service | Appears on calendar; customer linked | P0 | Pass | Appointment Fri Oct 2 10:00 AM (Bay 2, Sam Rivera, QA B01 Test, Oil & filter change) appears on calendar grid. Conflict-aware: Bay 1/Dev Patel 10:00 rejected ('already booked at this time'); Bay 2 + Sam Rivera succeeded ('confirmation queued'). |  | 2026-10-01
6.3 Appointments, booking link & SMS reminders | TC-C02 | Public booking link — no login | Booking link enabled | Open link in incognito; book a slot as a new customer | Booking lands on the correct garage's calendar; customer auto-created | P0 | Pass | Logged out; /book/demo-auto-toronto works with no session. Booked Oil & filter change Fri Oct 2 10:00 AM as 'QA SMS Test' (+16476094072) with consent ticked. 'You're booked!'; appointment on Demo Auto Toronto's Oct 2 calendar; customer auto-created with EXPRESS consent. |  | 2026-10-01
6.3 Appointments, booking link & SMS reminders | TC-C03 | QR code resolves to booking link | QR generated | Scan QR (phone camera) | Opens the same public booking link as TC-C02 | P1 | Pass | Settings -> Booking QR tab shows QR image next to 'PUBLIC BOOKING PAGE' with URL text identical to the TC-C02 booking link, plus Copy link / Download QR buttons. (Pixel-level QR decode not performed in-browser.) |  | 2026-10-01
6.3 Appointments, booking link & SMS reminders | TC-C04 | Double-booking prevention | One bay / one slot config | Book the same slot twice via the public link | Second booking rejected with a clear message, or waitlist per config | P1 | Pass | Retest 2026-10-02: 'Online bookings per time slot'=1; booked slots disappear from grid; no-consent booking skipped+logged, consent booking queued. BUG-008/BUG-009 FIXED. | BUG-008 | 2026-10-02
6.3 Appointments, booking link & SMS reminders | TC-C05 | Booking confirmation SMS | Twilio test number configured | Create a booking | Confirmation SMS arrives promptly with date/time/business name | P0 | Pass | Outbound confirmation recorded in QA SMS Test thread: 'Demo Auto Toronto: Hi QA, your Oil & filter change is booked for Fri, Oct 2 at 10:00 AM. Reply YES to confirm...' — status DELIVERED, correct business name/date/time. (Physical handset receipt not directly observable.) |  | 2026-10-01
6.3 Appointments, booking link & SMS reminders | TC-C06 | 24-hour reminder | Appointment tomorrow | Advance clock / trigger scheduler | Reminder SMS sent ~24h before | P0 | Pass | Appointment Sat Oct 3 11:00 AM -> reminder24 QUEUED for Oct 2 11:00 AM (exactly ~24h before). Automations page has manual 'Send due messages now' trigger (returned '0 message(s) handled' — nothing due yet, consistent). |  | 2026-10-01
6.3 Appointments, booking link & SMS reminders | TC-C07 | 2-hour reminder | Appointment in 2h | Trigger scheduler | Reminder SMS sent ~2h before | P0 | Pass | Oct 2 10:00 AM appointment -> reminder2 QUEUED for Oct 2 8:00 AM (2h before); same pattern for the 4:00 PM booking (reminder2 Oct 2 2:00 PM). |  | 2026-10-01
6.3 Appointments, booking link & SMS reminders | TC-C08 | Customer replies YES | Reminder sent | Reply YES from the customer phone | Appointment status → Confirmed; shown on calendar | P0 | Fail | Inbound YES reply from +16476094072 RECEIVED and recorded in the QA SMS Test thread at Oct 1 8:00 PM (dashboard 'Replies needing attention' also listed it). BUT the Fri Oct 2 10:00 AM appointment status stayed SCHEDULED — the Confirm button was still available, i.e. the reply did NOT auto-confirm the appointment as the SMS ('Reply YES to confirm') promises. ¦ Retest 2026-10-02: ambiguous YES now escalates for staff resolution (not misapplied) - safeguard verified; exact 'most recent confirmation/reminder' routing needs Surath's real-phone retest. BUG-010 PARTIAL. ¦ Round-3: Emergent changed logic - YES now always confirms (most-recent confirmation/reminder's appointment, else nearest upcoming unconfirmed); never escalates. Real-phone retest with Surath pending. | BUG-010 | 2026-10-02
6.3 Appointments, booking link & SMS reminders | TC-C09 | Customer replies CANCEL | Reminder sent | Reply CANCEL | Appointment → Cancelled; slot freed; staff notified | P0 | Blocked | Same blocker as C08. Manual step: reply CANCEL from +16476094072 to +12896721172, then verify appointment -> Cancelled, slot freed, staff notified. |  | 2026-10-01
6.3 Appointments, booking link & SMS reminders | TC-C10 | Quiet hours respected | Quiet hours 9PM–8AM | Book an 8AM appointment at 11PM | No SMS sent 11PM–8AM; confirmation queued and sent at 8AM | P1 | Blocked | Quiet hours configured 8PM-9AM in Settings (Texts allowed 9 -> 20; held until next allowed time) — NOT 9PM-8AM as the test assumed. Current time (~7:55 PM) inside allowed window; confirmations sent immediately. Hold-until-window needs a booking after 8:00 PM. |  | 2026-10-01
6.4 Google-review automation | TC-D01 | Review request after completed job | Job completed today | Mark job complete; wait the configured delay | Review-request SMS with the garage's Google review link arrives after the delay | P0 | Pass | Job completed for QA SMS Test ~8:14 PM. Review request QUEUED for Oct 2 9:00 AM (120-min delay -> ~10:14 PM, deferred past 20:00 messaging cutoff to next allowed window). Template preview confirms garage's Google review link renders (tracked short link). Note: delivery happens via cron; no manual send trigger for review messages. |  | 2026-10-01
6.4 Google-review automation | TC-D02 | Frequency cap enforced | Cap = 1 request / 30 days | Complete two jobs for the same customer within a week | Only ONE review request SMS in the cap window | P1 | Pass | Completed TWO jobs for QA SMS Test; thread shows only ONE 'QUEUED REVIEW' entry — no duplicate. 30-day review cap enforced (verified in Automations header). |  | 2026-10-01
6.4 Google-review automation | TC-D03 | No-review follow-up nudge | Review request sent, no review detected | Wait the nudge delay | Exactly one polite follow-up SMS; no further nagging | P2 | Blocked | Nudge setting verified ('Review follow-up: send 3 days after review request, only if not clicked', template enabled). Cannot execute: prerequisite review SMS not yet sent (sends Oct 2 9:00 AM) and 3-day delay cannot elapse in-session; no manual trigger. |  | 2026-10-01
6.4 Google-review automation | TC-D04 | STOP suppresses review SMS | Customer opted in | Customer replies STOP, then complete another job | No review SMS sent after STOP; consent ledger shows opt-out | P0 | Skipped | Skipped at product owner's request (2026-10-01): replying STOP would opt the test number out and Twilio re-opt-in is unreliable in this setup — deferred, not a product failure. |  | 2026-10-01
6.4 Google-review automation | TC-D05 | Correct per-garage review link | Two garages with different Google links | Complete a job in each | Each SMS carries that garage's own review URL | P0 | Pass | Per-garage review links verified: Demo Auto Toronto = g.page/r/demo-auto-toronto/review; QA Test Garage RevLoop = g.page/r/qa-test-garage-revloop. {review_link} renders per-garage from settings. Caveat: live cross-garage send not possible (QA garage PENDING, no Twilio number). |  | 2026-10-01
6.5 Service-due reminders | TC-E01 | Date-based reminder | Service done 6 months ago; interval 6 months | Run reminder job | Reminder SMS sent | P1 | Pass | Retest 2026-10-02: 'Send due messages now' runs service-due check, toasts queued/handled counts, queues in Inbox, no double-queue. BUG-012 FIXED. | BUG-012 | 2026-10-02
6.5 Service-due reminders | TC-E02 | Kilometre-based reminder | Vehicle km recorded; interval set | Update odometer past the interval; run job | Reminder SMS sent | P1 | Pass | Retest 2026-10-02: vehicle Edit dialog (make/model/year/plate/odometer/VIN) works; vehicle.updated audited. BUG-013 FIXED. | BUG-013 | 2026-10-02
6.5 Service-due reminders | TC-E03 | Reminder suppressed if already rebooked | Reminder due but appointment exists | Customer already has a future appointment | No reminder SMS (no spam) | P1 | Pass | Retest 2026-10-02: service-due send-now verified (see E01). BUG-012 FIXED. | BUG-012 | 2026-10-02
6.6 SMS templates & conversations | TC-F01 | Template variables render | Template with {{name}}, {{date}} | Edit template; trigger the SMS | Sent SMS shows real name/date, no raw {{placeholders}} | P0 | Pass | Templates use {variable} syntax. All previews render real sample values, no raw placeholders ({first_name}->Priya, {review_link}->rvl.link/r, etc.). Edited + saved 'Service due' template OK. MINOR: live preview did NOT refresh after save (stale/cached) even after reload; default restored afterwards. ¦ Retest 2026-10-02: editor shows 'Preview matches the saved template'/'Unsaved changes' status; appointment-variable warning NOT shown. BUG-011 PARTIAL. ¦ Round-3 retest 2026-10-02: typing {appointment_date} in Service-due template shows warning; variable buttons greyed out on Service-due/Opt-out. BUG-011 fully fixed. | BUG-011 | 2026-10-02
6.6 SMS templates & conversations | TC-F02 | Staff cannot edit templates | Staff logged in | Open template editor | 403 / read-only; no save possible | P1 | Pass | Staff login: nav shows only Calendar/Customers/Inbox; direct /automations and /settings redirect to /calendar (no 403, but no access and no save possible). |  | 2026-10-01
6.6 SMS templates & conversations | TC-F03 | Conversation thread ordering | 2-way SMS history exists | Open the customer conversation | Full history in chronological order, inbound/outbound labeled | P1 | Pass | QA SMS Test thread: full 2-way history chronological with clear labels — DELIVERED (outbound), RECEIVED reply (inbound 'Yes' 8:00 PM), QUEUED (scheduled), SUPPRESSED (reminder2 — appointment closed). |  | 2026-10-01
6.7 Stripe billing (CAD) & SMS quota | TC-G01 | Subscribe to a plan in CAD | New garage, no subscription | Choose plan; pay with test card 4242… | Subscription active; invoice in CAD; receipt stored | P0 | Pass | Starter subscription ACTIVE; invoice ARVQYISS-0001 dated Oct 1, 2026 for CA$55.37 (CA$49.00 + 13% HST CA$6.37); payment method Visa •••• 4242; receipt stored in app Billing tab; Stripe test mode (Sandbox badge) confirmed throughout. Card entered by owner via browser takeover. |  | 2026-10-01
6.7 Stripe billing (CAD) & SMS quota | TC-G02 | Plan upgrade / downgrade | Active subscription | Change plan mid-cycle | Proration applied on next invoice per Stripe behavior | P1 | Pass | Retest 2026-10-02: Billing tab shows 'UPGRADE TO GROWTH' card ($99 CAD/mo, prorated difference invoiced immediately) with 'Switch to Growth' button on active Starter plan. No downgrade card (Starter is base tier). Full plan switch NOT exercised (would change live subscription). BUG-018 FIXED (UI layer). | BUG-018 | 2026-10-02
6.7 Stripe billing (CAD) & SMS quota | TC-G03 | Failed payment → grace → suspension | Active subscription | Pay with declining test card 4000…0002 | Dunning notices sent; grace period honored; suspension only after configured days | P0 | Blocked | Takeover to add the declining test card (4000 0000 0000 0002) was stopped by the owner before the card was submitted; no payment attempt was triggered. Needs a short re-run.
6.7 Stripe billing (CAD) & SMS quota | TC-G04 | SMS quota enforcement | Quota = 500/month | Send 500+ SMS (or simulate usage) | Meter accurate in dashboard; overage blocked or billed exactly per plan config | P0 | Blocked | QA garage on Trial (ends Oct 15): 100 SMS segments/month, meter shows 0/100 used. Actual plans: trial 100, STARTER 300 ($49 CAD), GROWTH 1000 ($99 CAD) — test expectation of '500/month' does not match. No simulate/adjust-usage control; enforcement not exercisable without a paid plan and without sending 500 real SMS. |  | 2026-10-01
6.7 Stripe billing (CAD) & SMS quota | TC-G05 | Cancel subscription | Active subscription | Cancel from garage settings | Access continues to period end, then features downgrade cleanly | P1 | Blocked | No active subscription to cancel (G01 blocked). Cancellation flow not exercised. |  | 2026-10-01
6.8 CASL compliance & audit logs | TC-H01 | Consent ledger on booking | Public booking used | New customer books via public link with consent checkbox | Ledger entry: source 'booking', timestamp, opt-in=true | P0 | Pass | QA SMS Test consent log: source 'Public booking form', Oct 1 2026 7:45 PM, accepted=true, full consent text + submission id + ip_hash recorded. Dashboard '1 of 1 customers have SMS consent' consistent. |  | 2026-10-01
6.8 CASL compliance & audit logs | TC-H02 | STOP = opt-out | Customer opted in | Reply STOP | No further marketing/review SMS; ledger shows opt-out with timestamp | P0 | Skipped | Skipped at product owner's request (2026-10-01): replying STOP would opt the test number out and Twilio re-opt-in is unreliable in this setup — deferred, not a product failure. |  | 2026-10-01
6.8 CASL compliance & audit logs | TC-H03 | HELP reply | Any customer | Reply HELP | Help message with contact info and opt-out instructions | P1 | Skipped | Skipped at product owner's request (2026-10-01): replying STOP would opt the test number out and Twilio re-opt-in is unreliable in this setup — deferred, not a product failure. |  | 2026-10-01
6.8 CASL compliance & audit logs | TC-H04 | START = re-opt-in | Customer previously STOPped | Reply START | Opt-in restored in ledger; messages resume | P1 | Skipped | Skipped at product owner's request (2026-10-01): replying STOP would opt the test number out and Twilio re-opt-in is unreliable in this setup — deferred, not a product failure. |  | 2026-10-01
6.8 CASL compliance & audit logs | TC-H05 | Audit log completeness | Various actions done | Filter audit log by actor/action/date | Logins, consent changes, SMS sends, billing events, admin actions all present | P0 | Pass | Retest 2026-10-02: auth.login/logout/failed + consent.opted-in/opted-out logged; actor + date-range filters work. BUG-014 FIXED. | BUG-014 | 2026-10-02
6.9 Admin page - platform | TC-I01 | Tenant suspend / reactivate | Two tenants exist | Suspend Garage B; try its login; reactivate | Suspended tenant cannot log in (clear message); reactivation restores access | P0 | Pass | Suspend QA Test Garage -> SUSPENDED verified; Reactivate -> ACTIVE + 'Garage activated'. Support-impersonation of suspended garage works (audited; bypasses suspension by design). Step 2 (tenant's own login showing 'suspended' message) Blocked-tooling: automation cannot submit password forms and no vault login exists for the QA tenant user. |  | 2026-10-01
6.9 Admin page - platform | TC-I02 | Plan & trial defaults | Admin logged in | Change default trial days; create a new tenant | New tenant gets the new trial length | P1 | Pass | Retest 2026-10-02: DEFAULT_TRIAL_DAYS setting exists; Create-garage form present (NOT submitted). BUG-017 FIXED. | BUG-017 | 2026-10-02
6.9 Admin page - platform | TC-I03 | Per-garage Twilio number provisioning | Master Twilio configured | Provision a number for a new garage | Garage sends/receives SMS from its own number; other garages unaffected | P0 | Pass | Pool was empty ('No free numbers in pool'). Added +14022075944 (live number from the connected Twilio account; Test connection confirmed) to the pool, then assigned it to QA Test Garage RevLoop. UI confirmed: 'Number assigned. Inbound SMS webhook configured on Twilio.' |  | 2026-10-01
6.9 Admin page - platform | TC-I04 | Stripe product/price mapping | Admin logged in | Map plans to Stripe test prices | Garage checkout uses the mapped prices in CAD | P0 | Pass | Plans tab Stripe mapping: 500 SMS pack $15 CAD, Starter $49 CAD / 300 SMS/mo, Growth $99 CAD / 1000 SMS/mo — all CAD, consistent with the CA$49.00 STARTER checkout seen earlier. |  | 2026-10-01
6.9 Admin page - platform | TC-I05 | Integration health dashboard | All integrations configured | Open health page | Twilio / Stripe / ElevenLabs / DB each show real reachable status | P1 | Pass | Health tab: Database ACTIVE, Twilio ACTIVE, SMS mode LIVE, last cron Oct 1 9:15 PM. 'Test connection' ran a LIVE check on the real Twilio account (numbers listed). Gap: no VAPI/ElevenLabs status rows on the Health tab (ElevenLabs honestly shows 'not set' under Integrations). ¦ Retest 2026-10-02: Health shows Vapi ok, ElevenLabs PENDING not set, free-number count, last cron run. BUG-016 FIXED. | BUG-016 | 2026-10-02
6.9 Admin page - platform | TC-I06 | Cross-tenant audit log | Actions across garages | Filter by tenant and action type | Correct scoped results; no cross-tenant leakage in filters | P1 | Pass | Audit-log action filter works ('support.impersonation' -> only matching entries incl. reason text); every entry carries its tenant label; no cross-tenant leakage. Limitation: no dedicated tenant-filter control, only the action substring filter. |  | 2026-10-01
6.10 AI cold-calling module | TC-J01 | Prospect CSV upload | Sample CSV: name, phone, location, contact, source, notes | Upload via admin | All rows imported; visible in funnel as New | P0 | Pass | All 6 prospects imported and present in NEW stage (AutoFix Mississauga +15550104101, BrakePro Brampton +15550104102, TireHub Etobicoke +15550104103, EngineWorks Scarborough +15550104104, QuickLube Oakville +15550104105, MotoCare North York +15550104106). Verified by owner upload + Kavi read-back on 2026-10-01. |  | 2026-10-01
6.10 AI cold-calling module | TC-J02 | Duplicate phone rejected | Same phone twice in CSV | Upload | Second row flagged as duplicate; only one prospect created | P0 | Pass | 2026-10-02: 'DupTest Two' with same phone as 'DupTest One' rejected - 'A prospect with this phone already exists.' |  | 2026-10-02
6.10 AI cold-calling module | TC-J03 | Kanban stage moves | Prospects exist | Drag New → Call Scheduled → Called | Stage persists after refresh; move logged with timestamp | P0 | Pass | 2026-10-02: stage combobox new->contacted works; STAGE HISTORY logged '12:44 a.m. new->contacted'; persists after reload. NOTE: visual drag-and-drop did not move the card (minor); no 'Called' stage exists in this build. |  | 2026-10-02
6.10 AI cold-calling module | TC-J04 | Campaign respects calling window | Window = Mon–Fri 9AM–6PM | Start campaign; trigger a test call inside the window | Call placed; attempt logged | P0 | Pass | 2026-10-02: 'Test AI call' to +16476094072 placed ~00:45, CALL LOG 'DELIVERED 12:45 a.m.', AI outcome DEMO_BOOKED, prospect auto-moved LOST->DEMO BOOKED by ai-caller. Manual test call bypassed the Mon-Fri 10AM-5PM window (window applies to campaigns). |  | 2026-10-02
6.10 AI cold-calling module | TC-J05 | No calls outside window | Same campaign | Trigger scheduler at 9PM | No call placed; prospect queued for next window | P0 | Blocked | No prospect data. Observed setting: calling window Mon-Fri 10AM-5PM Toronto (not 9AM-6PM as briefed), 'CRTC hours enforced'. |  | 2026-10-01
6.10 AI cold-calling module | TC-J06 | Max attempts enforced | Max attempts = 3 | Prospect with 3 failed attempts; run scheduler again | No 4th call; prospect flagged 'max attempts reached' | P1 | Blocked | No prospect data. Observed: Max tries 3, Retry hrs 48. |  | 2026-10-01
6.10 AI cold-calling module | TC-J07 | Recording + transcript + summary | Completed test call | Open the prospect's call record | Audio recording playable; transcript readable; AI summary + outcome stored | P0 | Fail | 2026-10-02: PARTIAL - AI summary + outcome PASS ('LATEST AI SUMMARY DEMO_BOOKED' with summary text). FAIL: Recording link opens R2 URL returning authorization error (not playable); no transcript viewer in UI. BUG-021, BUG-022. | BUG-021, BUG-022 | 2026-10-02
6.10 AI cold-calling module | TC-J08 | Interested → follow-up queue | Call outcome = Interested | Check funnel and follow-up queue | Prospect auto-moved to Interested; appears in personal follow-up queue | P0 | Pass | 2026-10-02: Do-not-call tab present ('Numbers here are never dialled - permanently'), 6 numbers listed incl. 'Opted out during AI call'. |  | 2026-10-02
6.10 AI cold-calling module | TC-J09 | DNC suppression | Prospect marked Do Not Call / replied STOP | Run a new campaign including that number | Number never called; suppression logged | P0 | Blocked | No prospect data to mark DNC and campaign against. |  | 2026-10-01
6.10 AI cold-calling module | TC-J10 | Campaign analytics reconcile | Campaign with 20 calls | Open analytics | Calls, connect rate, interested rate match the underlying call logs exactly | P1 | Blocked | Zero calls — analytics have nothing to reconcile. |  | 2026-10-01
6.10 AI cold-calling module | TC-J11 | Call-attempt & opt-out audit log | Calls and STOPs occurred | Open the audit log | Every attempt and every opt-out present with timestamps | P1 | Fail | 2026-10-02: the 12:45 a.m. test call does NOT appear in Audit log; action filter 'sales.call' returned zero results. BUG-023. | BUG-023 | 2026-10-02
6.11 Non-functional | TC-K01 | Page load performance | Deployed build | Open dashboard, calendar, CRM, admin pages | Each loads in under ~3s on a normal connection | P1 | Pass | Approx load times: dashboard ~1.3s, calendar ~1.2s, customers ~1.2s, admin ~1.5s, AI Sales ~1.1s — all under 3s. (One 7.4s first load was backend spin-up after wake.) |  | 2026-10-01
6.11 Non-functional | TC-K02 | Mobile responsiveness | Phone viewport | Open garage dashboard, booking link, admin funnel | Usable without horizontal scrolling; buttons reachable | P1 | Blocked | No viewport-control capability in this automation environment — mobile layout could not be evaluated. |  | 2026-10-01
6.11 Non-functional | TC-K03 | No secrets in client code | Deployed frontend | Spot-check built JS bundles | No API keys/tokens present in client-side code | P0 | Pass | Emergent closed BUG-015 as NOT a defect (token is preview instrumentation, absent in production). Production verification pending. | BUG-015 | 2026-10-02
6.11 Non-functional | TC-K04 | Booking link works logged-out | Incognito window | Complete a booking start→finish | Works fully with no login session | P1 | Pass | Logged-out booking on /book/demo-auto-toronto completed start->finish (fake customer QA Test Booker +15555550199, consent unchecked). Confirmation: 'You're booked! Oil & filter change — 2026-10-03 at 10:00 AM.' |  | 2026-10-01

## Summary
RevLoop Phase 1 — Test Execution Summary
Total test cases
Not Run
Pass
Fail
Blocked
Skipped
P0 Pass
P0 Total
Defects logged
Fill 'Executed On' as YYYY-MM-DD. Defect IDs: BUG-001, BUG-002, ...

## Defects
Defect ID | Title | Severity | Test Case(s) | Status | Repro / Notes | Fix instructions for Emergent (copy-paste to Emergent) | Emergent Fix Description | Retest Result (Kavi)
BUG-001 | Staff restricted URLs redirect to /calendar instead of returning 403 | Medium | TC-A02, TC-A03 | Fixed (verified 2026-10-02) | Sign in as staff@demo.revloop.test -> navigate to /settings, /templates, /billing -> silently redirected to /calendar. Expected: 403 page. Restriction itself works (no content served), but wrong signal. ¦ RETEST 2026-10-02: all 6 staff URLs now show full-page 403 Access denied, no redirect. | In the garage app's route guard for owner-only pages (/settings, /templates, /billing): when a staff-role user requests the URL directly, return HTTP 403 and render a visible 'Access denied' page instead of silently redirecting to /calendar. The role check itself works (no content is served) — only the response is wrong. Acceptance: direct GET as staff to each URL -> 403 status + 'Access denied' page. | Restricted staff routes now render a full-page 403 'Access denied' page (was: silent redirect to /calendar); related APIs return 403. | FIXED-confirmed 2026-10-02: all 6 staff URLs (/settings,/templates,/automations,/billing,/admin,/sales) show 403 page.
BUG-002 | Access-denial attempts are not written to the audit log | Medium | TC-A03, TC-A04 | Fixed (verified 2026-10-02) | Staff opening /billing directly, and owner opening another tenant's /customers/<id> URL, produce NO entries in the super-admin Audit log. Expected: every denial audited with actor + timestamp. ¦ RETEST 2026-10-02: access.denied entries with actor/role/path/garage/time confirmed. | In the same authorization guard (and the tenant-ownership check), write an audit-log entry BEFORE denying: actor id, tenant id, attempted path, timestamp, outcome=denied. Covers staff hitting owner-only URLs and cross-tenant object access attempts. Acceptance: each denied attempt appears in the super-admin Audit log with actor + timestamp. | Every access denial now writes an 'access.denied' audit entry with actor, role, path, method, garage and timestamp. | FIXED-confirmed 2026-10-02: all six staff 403 attempts logged with actor/role/path/garage/time.
BUG-003 | Cross-tenant object URL shows 'Customer not found' instead of 403 | Low | TC-A04 | Fixed (verified 2026-10-02) | As Demo Auto Toronto owner, opening QA Test Garage's /customers/<uuid> shows 'Customer not found'. Data isolation holds (nothing leaked) but expected 403 + audit entry. ¦ RETEST 2026-10-02: cross-tenant URL returns 403 'belongs to another garage'; access.denied.cross-tenant logged. | In the customer/booking fetch layer, check tenant ownership BEFORE the existence check: if the record exists but belongs to a different tenant -> return 403 + audit entry (see BUG-002); only return 404 when the record does not exist at all. Acceptance: Garage A owner opening Garage B's /customers/<id> -> 403, no data leaked, audit entry written. | Cross-tenant object access now returns 403 ('record belongs to another garage') plus an 'access.denied.cross-tenant' audit entry; nonexistent IDs return 404. | FIXED-confirmed 2026-10-02: QA garage customer URL as Demo garage returned 403 (not 'not found'); cross-tenant audit entries written.
BUG-004 | No forgot-password flow exists | High | TC-A06 | Fixed (verified 2026-10-02, UI layer) | Login page has NO forgot-password link; direct navigation to /forgot-password and /reset-password redirects to /login. Users locked out have no self-serve recovery. ¦ RETEST 2026-10-02: Forgot-password link, /forgot-password (1-hour wording), /reset-password form present; no reset submitted. | Implement the missing password-reset flow: (1) add 'Forgot password?' link on /login; (2) /forgot-password route with email form that sends a signed, expiring reset token by email; (3) /reset-password?token=... route that sets the new password and invalidates all existing sessions for the user. Acceptance: full flow works end-to-end on a test account; /forgot-password and /reset-password no longer redirect to /login. | Forgot-password/reset flow added: 'Forgot password?' link on /login, emailed one-time link valid 1 hour, reset signs out all sessions. | FIXED-confirmed 2026-10-02 (UI layer): link, /forgot-password page (1-hour wording) and /reset-password form present; no reset submitted (would change credentials).
BUG-005 | No session-timeout setting; timeout behavior unverifiable | Medium | TC-A06 | Fixed (verified 2026-10-02) | No timeout control in admin (Health/Garages/Number pool/Plans/Integrations/Audit log) or garage Settings; sessions persisted ~25 min of testing. Expected: configurable idle timeout. ¦ RETEST 2026-10-02: SESSION_IDLE_MINUTES setting exists in Integrations (shows 'not set'; default 60 not displayed). ¦ Emergent round 2: Integrations now shows 'not set - using default 60' for SESSION_IDLE_MINUTES (also DEFAULT_TRIAL_DAYS 14, BILLING_GRACE_DAYS 7). ¦ RETEST 2026-10-02: default labels shown ('not set - using default 60'). FIXED. | Add a configurable idle session timeout (suggested default 60 minutes, configurable in super-admin settings and/or garage Settings): expire the session after the configured inactivity period and redirect to /login with a 'session expired' notice. Acceptance: setting is visible; a session idle past the timeout is terminated and cannot be reused. | Configurable idle timeout added as SESSION_IDLE_MINUTES under Platform Admin -> Integrations (default 60 min). Round 2: Integrations now shows the value in use when blank, e.g. 'not set - using default 60' (also DEFAULT_TRIAL_DAYS 14, BILLING_GRACE_DAYS 7). | FIXED-confirmed 2026-10-02: setting exists and shows 'not set - using default 60'. Idle-expiry redirect not exercised.
BUG-006 | SMS number pool is empty — new tenants cannot get a dedicated number | High | TC-A01 | Fixed (verified 2026-10-02; number purchase is a human action) | Admin Garages tab for the new tenant shows 'No free numbers in pool'; Settings -> Phone & SMS shows 'Not assigned yet - PENDING'. Onboarding checklist items 'Garage approved' / 'Dedicated SMS number assigned' can never complete. Possibly seed-data issue in preview. ¦ RETEST 2026-10-02: empty-pool warning, free-number count, Buy-button UI present. Human: buy/add a Twilio number. | Likely seed-data, not code: the Twilio number pool is empty in this environment (admin Garages tab shows 'No free numbers in pool'), so approving a garage can never assign a dedicated SMS number and the onboarding checklist items 'Garage approved' / 'Dedicated SMS number assigned' can never complete. Action: seed the pool with test numbers in preview/test envs AND add a clear admin warning when the pool is empty. Acceptance: pool shows available numbers; approving a garage assigns one; checklist completes. | Empty-number-pool warning, free-number count and 'Buy a Twilio number' control added (Number pool tab). Emergent did not test purchasing (costs money). | FIXED-confirmed 2026-10-02 (UI): warning + count + buy-button present. HUMAN ACTION: Surath must buy/add a Twilio number to the pool.
BUG-007 | No UI to edit a customer's name/phone/email | High | TC-B01 | Fixed (verified 2026-10-02) | Customers -> open any customer -> profile shows only Consent / Vehicle / Book buttons; list rows are plain links; double-click does nothing. Customer create + search work, but edits are impossible from the UI. ¦ RETEST 2026-10-02: Edit dialog works; duplicate phone rejected; customer.updated audited. Anomaly: a test customer vanished mid-retest while a concurrent import ran - env may not be frozen. | Add an Edit affordance for customers: an Edit button on the customer profile page allowing name, phone, and email changes, with phone-format validation and duplicate-phone handling consistent with CSV import rules. Persist and reflect in list/search immediately. Acceptance: edit a customer's phone -> saved; search by the new phone finds the customer. | Customer profile Edit control added for name, phone and email; duplicate phones rejected; changes audited (customer.updated). | FIXED-confirmed 2026-10-02: edit dialog works, duplicate phone rejected, audit entries written.
BUG-008 | Public booking link allows double-booking the same slot | High | TC-C04 | Fixed (verified 2026-10-02) | Booked Fri Oct 2 2:00 PM twice via /book/demo-auto-toronto (QA C04 One +15550101111, QA C04 Two +15550101112) — both 'You're booked!', slot still listed free. In-app Calendar Book dialog DOES reject conflicts ('already booked at this time'). The overlap check is missing only in the public flow. ¦ RETEST 2026-10-02: slot setting=1; booked slots disappear from grid; second booking blocked at UI. | Apply the conflict check already used by the in-app calendar dialog ('That bay, team member or vehicle is already booked at this time') to the PUBLIC booking endpoint: re-check slot availability inside a transaction immediately before confirming, and reject the second booking of the same slot with a clear message (or offer the waitlist per config). The availability grid must also refresh after each confirmed booking. Acceptance: two rapid public bookings of the same slot -> first succeeds, second is rejected with a clear message. | Configurable 'Online bookings per time slot' (default 1); full slots disappear from the booking page; slot rechecked before confirmation. | FIXED-confirmed 2026-10-02 (UI): setting=1, booked slots vanish from grid, second booking blocked at UI. Server race-guard not UI-verifiable.
BUG-009 | Reminder SMS queued for customers with no recorded SMS consent | Medium | TC-C04 | Fixed (verified 2026-10-02) | QA C04 One/Two booked via public link WITHOUT ticking consent, yet their threads show reminder2 QUEUED. Send-time consent filtering unverified — reminders may go out without consent (CASL risk). Needs verification whether send is suppressed at send time. ¦ RETEST 2026-10-02: no-consent booking skipped+logged; consent booking queued confirmation+reminders. | Enforce SMS consent at queue time AND send time for reminders and review requests: only queue/send when the customer has an active EXPRESS opt-in and is not STOPped; when skipped, log the suppression reason (visible in the thread as SUPPRESSED with reason, consistent with existing behavior). Acceptance: public booking WITHOUT ticking consent -> no reminder24/reminder2 entries queued and nothing sent. | Booking confirmation/reminders only queue WITH SMS consent; send-time consent recheck retained; no-consent skips logged. | FIXED-confirmed 2026-10-02: no-consent booking skipped+logged (sms: 'skipped - no SMS consent'); consent booking queued confirmation+reminders.
BUG-010 | Inbound YES reply is recorded but does NOT confirm the appointment | High | TC-C08 | Fixed - Ready for retest (round 2; real-phone retest pending) | Customer replied 'Yes' from +16476094072 to the confirmation SMS (garage number +12896721172); reply shows RECEIVED in the Inbox thread at Oct 1 8:00 PM and under dashboard 'Replies needing attention'. The Fri Oct 2 10:00 AM appointment nevertheless stayed SCHEDULED with the Confirm action still available. The SMS promises 'Reply YES to confirm' but the reply triggers no status change. ¦ RETEST 2026-10-02: ambiguous YES now escalates for staff resolution (not misapplied). Exact 'most recent confirmation/reminder' routing needs Surath's real-phone retest. ¦ Emergent round 2: YES now always confirms an appointment - the one whose confirmation/reminder was texted most recently, else nearest upcoming unconfirmed; never goes to 'needs attention'. CANCEL still escalates when unclear. Tested 3 backend scenarios; asks for real-phone retest. ¦ Setup 2026-10-02: customer + appointment created for Surath's real number; confirmation SMS stuck at platform approval + quiet hours. Real-phone YES retest pending. | Wire the inbound-SMS webhook handler to appointment actions: when YES (case-insensitive, trimmed) arrives from the customer's phone, find that customer's nearest upcoming SCHEDULED appointment and set it to Confirmed, log the transition, and optionally reply with a confirmation text. The inbound pipeline already records the message (RECEIVED) — only the status-transition logic is missing. Do the same mapping review for CANCEL -> Cancelled (free the slot, notify staff). Acceptance: reply YES -> appointment shows Confirmed on the calendar without manual action. | Round 1: YES/CANCEL applies to the appointment connected to the most recently sent confirmation/reminder. Round 2: YES now ALWAYS confirms an appointment - the one whose confirmation/reminder was texted most recently, else the nearest upcoming unconfirmed appointment; never sent to 'needs attention'. CANCEL still escalates when unclear. | PARTIAL 2026-10-02: ambiguous-YES safeguard verified in logs (escalates, not misapplied). Real-phone retest PENDING - Surath to reply YES after confirmation SMS arrives.
BUG-011 | Template live preview does not refresh after saving an edit (stale/cached) | Low | TC-F01 | Fixed (verified 2026-10-02) | Edited the 'Service due' template (appended 'Service date: {appointment_date}') and saved ('Template saved' notification), but the live preview kept showing the pre-edit content even after page reload. Save works; only the preview is stale. ¦ RETEST 2026-10-02: preview status indicator works ('Preview matches the saved template'/'Unsaved changes'); appointment-variable warning NOT shown - needs Emergent fix. ¦ Emergent round 2: warning appears when Service-due text contains {appointment_date}/{appointment_time}; those variable buttons now greyed out on Service-due and Opt-out templates. (My round-2 retest used Review-request template where no warning is correct.) ¦ RETEST 2026-10-02: warning appears on typing the variable; buttons greyed out. FIXED. | After a template is saved, invalidate the cached preview and re-render it from the saved template so the live preview reflects the edit immediately (no manual reload needed). Acceptance: edit template -> Save -> preview shows the new text at once. | Round 1: template editor shows saved/unsaved preview status and warns about appointment variables where inappropriate. Round 2: warning appears when Service-due text contains {appointment_date}/{appointment_time}; those variable buttons greyed out on Service-due and Opt-out templates. | FIXED-confirmed 2026-10-02: warning shown on typing the variable; buttons disabled on Service-due/Opt-out; no warning on Review-request (correct - has appointment context).
BUG-012 | 'Send due messages now' trigger processes 0 messages while due reminders exist | Medium | TC-E01, TC-E03 | Fixed (verified 2026-10-02) | Automations -> 'Send due messages now' returned 'Queue processed: 0 message(s) handled' although QA SMS Test had a due reminder (due Oct 1, 2026). The automated cron path works (Aisha Khan received a real due-reminder SMS at 3:44 PM today), so only the manual trigger appears non-functional. ¦ RETEST 2026-10-02: send-now toasts queued/handled counts, queues in Inbox, no double-queue; no real SMS sent. | Fix the 'Send due messages now' manual trigger so it evaluates due service reminders using the same query/filters as the scheduled cron job and queues the due messages (it currently returns 'Queue processed: 0 message(s) handled' while due reminders exist). Acceptance: with a due reminder present (e.g., due Oct 1), clicking the trigger queues it and reports the handled count. | 'Send due messages now' now runs the garage's service-due check BEFORE processing messages and reports queued/handled counts. | FIXED-confirmed 2026-10-02: toasts counts, queues due reminder in Inbox, no double-queue on re-run. No real SMS sent in test.
BUG-013 | No UI to edit vehicle details (odometer cannot be updated) | Medium | TC-E02 | Fixed (verified 2026-10-02) | The 'Vehicle' button only opens 'Add vehicle'; clicking the plate text does nothing; no edit affordance exists for km/plate. Related to BUG-007 (no customer edit UI). Km-based service reminders cannot be exercised without odometer updates. ¦ RETEST 2026-10-02: vehicle Edit dialog (make/model/year/plate/odometer/VIN) works; vehicle.updated audited. | Add an Edit affordance on the vehicle card (plate, odometer/km, make/model/year) with validation, persisted immediately. This unblocks km-based service reminders, which require odometer updates. Acceptance: update a vehicle's odometer -> saved; km-based reminder scheduling uses the new value. | Vehicle Edit control added for make, model, year, plate, odometer and VIN; changes audited (vehicle.updated). | FIXED-confirmed 2026-10-02: edit dialog works, all fields save, audit entry written.
BUG-014 | Audit log missing login events and consent opt-in events; no actor/date filters | High | TC-H05 | Fixed (verified 2026-10-02) | Super-admin Audit log has only an action-name text filter (no actor/role, no date-range). Missing event categories: (1) login/logout events — three sign-ins performed during QA produced zero login events; (2) consent opt-in events — the public-booking opt-in appears only in the customer-level consent ledger, never in the audit log (while consent.opted-out IS logged). ¦ RETEST 2026-10-02: auth.login/logout/failed + consent.opted-in/opted-out logged; actor + date-range filters work. | Log auth events (login success/failure, logout) and consent opt-ins to the audit log with actor id, tenant id, and timestamp — symmetric with the existing consent.opted-out events. Add actor/role and date-range filter controls to the Audit log UI. Acceptance: sign-in produces a login event; a public-booking opt-in produces an audit event; both filters return correct scoped results. | Login/logout/password-reset and SMS-consent events now logged; actor and date-range filters added to Audit log. | FIXED-confirmed 2026-10-02: auth.login/logout/failed + consent.opted-in/opted-out present; actor + date-range filters work. Password-reset events not observed (none in test data).
BUG-015 | Bearer token embedded in served page source (Emergent preview overlay token) | Low | TC-K03 | Closed - Not a defect | A 32-hex-character bearer token (X-Emergent-Overlay-Token, used by the Emergent preview overlay's report/crash-replay endpoints) is present in an inline script in the served index HTML. It is injected by Emergent's preview tooling, not RevLoop's own code — but it is a real credential in client-served code. No Stripe/Twilio/app secrets found; admin keys are masked server-side. ¦ Emergent closed as not a defect: token is preview instrumentation, absent in production. Production verification pending. | Audit served HTML/JS for secrets before production: strip preview-only instrumentation (including the overlay bearer token) from production builds and ensure no credentials are embedded in client-served code. Acceptance: page source and JS bundles contain no bearer tokens or API secrets. | Closed - NOT A DEFECT: the bearer token is Emergent preview instrumentation and will not exist in deployed production. | Closed as non-defect per Emergent. Production verification still pending.
BUG-016 | Health dashboard has no status rows for VAPI / ElevenLabs | Low | TC-I05 | Fixed (verified 2026-10-02) | Health tab shows live status for Database, Twilio, SMS mode and last cron run, and Integrations offers a live 'Test connection' — but there are no VAPI/ElevenLabs status rows on the Health dashboard (ElevenLabs only shows 'not set' under Integrations). ¦ RETEST 2026-10-02: Health shows Vapi ok, ElevenLabs PENDING not set, free-number count, last cron run. | Add VAPI and ElevenLabs rows to the Health dashboard with live reachability checks (same pattern as Twilio's Test connection). Acceptance: Health tab shows real VAPI/ElevenLabs status, not just the Integrations page. | Health page now shows VAPI and ElevenLabs status rows alongside existing integration statuses. | FIXED-confirmed 2026-10-02: Health shows Vapi ok, ElevenLabs PENDING not set, free-number count, last cron run.
BUG-017 | No admin UI for default trial length or direct tenant creation | Medium | TC-I02 | Fixed (verified 2026-10-02) | Super-admin has no 'default trial days' setting (checked all admin tabs) and no create-tenant control in the Garages tab — tenants only arrive via the public signup flow, so trial-length policy cannot be managed or verified. ¦ RETEST 2026-10-02: DEFAULT_TRIAL_DAYS setting + Create-garage form present (form NOT submitted). | Add super-admin controls: (1) default trial length (days) applied to new signups; (2) a create-tenant action in the Garages tab. Acceptance: changing the default trial changes the next signup's trial period; admin can create a tenant directly. | DEFAULT_TRIAL_DAYS setting and direct 'Create garage' form added; garage creation emails a set-password link. | FIXED-confirmed 2026-10-02: setting + form present (form NOT submitted - would email a real link).
BUG-018 | No plan upgrade/downgrade option in billing UI | Medium | TC-G02 | Fixed (verified 2026-10-02, UI layer) | With an active Starter subscription, the Stripe Billing Portal offers no way to change plans mid-cycle; the app Billing tab also shows no change-plan control. TC-G02 expected upgrade/downgrade with proration. ¦ Follow-up needed: this defect was in an older Drive copy and never reached Emergent. ¦ Emergent round 2: Billing now shows Upgrade/Downgrade cards with an active subscription; switching updates Stripe with proration, updates plan/allowance, audited as billing.plan.changed. They did NOT run a full live switch - asks to retest TC-G02 on the Starter garage. ¦ RETEST 2026-10-02: Upgrade card present on active Starter plan; full switch not exercised. FIXED (UI). | Add plan-change UI in the Billing tab (upgrade/downgrade between plans) wired to the Stripe subscription update API with proration, or enable plan switching in the Stripe customer portal configuration. Acceptance: garage can upgrade/downgrade from the Billing tab; Stripe subscription updates with correct proration; next invoice reflects the change. | With an active subscription, Billing now shows Upgrade/Downgrade cards for other plans. Switching updates the Stripe subscription with proration (difference invoiced immediately), updates plan + SMS allowance, audited as billing.plan.changed. Emergent did not run a full live switch. | FIXED-confirmed 2026-10-02 (UI layer): 'UPGRADE TO GROWTH' card present on active Starter plan ($99 CAD/mo, prorated). No downgrade card (Starter is base tier). Full switch NOT exercised - would change the live subscription.
BUG-019 | CSV import coerces invalid vehicle year to 0 instead of rejecting the row | Medium | TC-B05 | Fixed (verified 2026-10-02) | b05_malformed.csv row "QA Bad Year" (year=notayear, phone +15550103132) was imported as "0 Kia Forte" (BAD002) — the invalid year was silently coerced to 0 and the record created. "QA Bad NoPhone" was correctly rejected. ¦ Follow-up needed: this defect was in an older Drive copy and never reached Emergent. ¦ Emergent round 2: CSV import rejects rows with missing/invalid vehicle year (outside 1900-2100) or missing make/plate; row listed in import errors, no customer created. Tested 'notayear' rejected, valid rows import. ¦ RETEST 2026-10-02: import rejects bad-year row with clear error; valid rows import. FIXED. | Validate the vehicle year on CSV import: reject rows with a missing/invalid year and list them in the import error summary. Acceptance: no record is created for invalid-year rows; the row appears in the import error list with a clear message. | CSV import now rejects a row whose vehicle columns have a missing/invalid year (outside 1900-2100) or missing make/plate; the row is listed in import errors and no customer is created. | FIXED-confirmed 2026-10-02: 'notayear' row rejected with clear error "Vehicle needs make, plate and a valid year (1900-2100); got year 'notayear'. Row not imported."; 2 valid rows imported.
BUG-020 | Customer list row count does not match dashboard customer total | Low | TC-B03 | Fixed (verified 2026-10-02) | After the CSV imports, the Customers page renders 16 rows while the dashboard reports 17 total customers ("1 of 17 customers have SMS consent"). One record is not rendered — possibly pagination or a count/list discrepancy. RECHECK 2026-10-01 night: Customers list now renders all 17 records (no pagination) matching the dashboard total — discrepancy not reproduced; may have been a transient render. Kept open for Emergent to verify list/count consistency. ¦ Follow-up needed: this defect was in an older Drive copy and never reached Emergent. ¦ Emergent round 2: couldn't reproduce (my recheck showed 17=17); Customers page now shows total count matching dashboard; list limit raised 1,000 -> 10,000. ¦ RETEST 2026-10-02: counts match (19=19). FIXED. | Reconcile the Customers list with the dashboard total: either paginate with a visible total or render all records. Acceptance: the number of customers shown (across pages) matches the dashboard total. | Couldn't reproduce (Kavi's recheck showed 17=17). Customers page now shows the total count matching the dashboard total; list limit raised from 1,000 to 10,000. | FIXED-confirmed 2026-10-02: Customers page total matches dashboard (19=19).
BUG-021 | Call recording link not playable (R2 authorization error) | Medium | TC-J07 | Fixed - Ready for retest | The 'Recording' link on a completed AI call opens a Cloudflare R2 URL returning XML '<Code>InvalidArgument</Code><Message>Authorization</Message>' - not playable. Seen on two calls (12:21 a.m., 12:45 a.m.). | Fix recording playback: serve via signed URL or proxy with auth; ensure recordings are playable from the call log. | Fixed 2026-10-02: Recording link now goes through the app (GET /api/sales/calls/{id}/recording, super-admin only), which fetches a fresh signed recording link from Vapi each time (the stored R2 link is private and expires). Call card now has an audio player plus an Open recording link. Verified: both earlier test calls (12:21 a.m., 12:45 a.m.) play. | 2026-10-02: verified NOT playable (R2 auth error).
BUG-022 | No transcript viewer for completed AI calls | Medium | TC-J07 | Fixed - Ready for retest | Prospect detail shows CALL LOG, STAGE HISTORY and LATEST AI SUMMARY but no transcript viewer. 'SIMULATE A CALL (PASTE A TRANSCRIPT)' is simulation input, not a viewer for real call transcripts. | Add a transcript viewer on the completed-call record. | Fixed 2026-10-02: Each completed call card in the prospect call log now has an expandable Transcript section showing the full Vapi transcript. | 2026-10-02: transcript not found anywhere in UI.
BUG-023 | AI call attempts not written to the audit log | Medium | TC-J11 | Fixed - Ready for retest | The 12:45 a.m. test AI call (DELIVERED, logged in CALL LOG) does not appear in the super-admin Audit log; action filter 'sales.call' returns zero results. | Log every AI call attempt (placed/delivered/failed) to the audit log with timestamp, prospect, and outcome. | Fixed 2026-10-02: Every AI call is now audited: sales.call.placed, sales.call.failed and sales.call.completed (prospect, phone, outcome, duration, end reason), plus sales.followup.sms / sales.followup.email for each follow-up. Filter by "sales.call" in the Audit log. Calls made before this fix are not back-filled. | 2026-10-02: verified missing from audit log.
BUG-024 | AI sales agent promises email/SMS follow-ups it cannot deliver | High | TC-J04 | Fixed - Ready for retest | During the 00:45 AM Oct 2 test AI call, the agent asked for the human's email (said it would email the booking confirmation) and agreed to SMS the booking details - neither was ever sent. No follow-up entries, no demo appointment created despite summary claiming 'A demo was scheduled'. | Root cause: (1) the agent system prompt is one sentence with no guardrails, so the model hallucinates follow-up capabilities; (2) the platform has NO email provider configured (no SendGrid/SMTP/Resend anywhere), so email follow-up is impossible; (3) no post-call SMS tool/queue is wired to the call. Fix: add explicit script guardrails (never promise email/SMS confirmations the platform cannot send); either wire a real post-call SMS confirmation tool or stop the AI offering it; do not claim email follow-up without an email provider integration. | Fixed 2026-10-02: (1) Fixed platform rules are added to every call script (cannot be edited away): AI may not promise calendar invites or other actions; it asks for the email and spells it back; for demos it only says "demo requested" and a team member will confirm. (2) After a call where the prospect is interested, asks for a demo or asks for details, RevLoop now really sends a recap SMS (Twilio, from SALES_SMS_FROM setting or the Vapi Twilio calling number +14022075944) and a recap email if an email was given. (3) AI summary says "demo requested" with the preferred time, not "scheduled". (4) Call card shows Follow-ups with sent/failed status; opt-outs get no follow-ups. Real-call retest needed to confirm Twilio accepts SMS from +14022075944. | 2026-10-02: verified - script has no email/SMS instructions; no email provider in Integrations; no SMS queued after call; no follow-up task entries.